## WSAB 2025-2027 Strategic Plan
Wildfire Safety Advisory Board Strategic Plan 2025-2027
The vision of the Wildfire Safety Advisory Board is a fire resilient California free of utility caused wildfires.
The mission of the Wildfire Safety Advisory Board is to advise and make recommendations to reduce the risk of utility related wildfires.
Priority | Objective | KPI | Action | Who | Milestones | [5 empty] | Last update: | 2025-05-14
[5 empty] | Q1 |  |  | Q2 | Q3 | Q4 |  | Objective Outcome/status
[5 empty] | Jun. | Jul. | Aug. | Sep. - Nov. 2025 | Dec. '25 - Feb. '26 | Mar. - May 2026 | Action Status
Priority 1: Actualizing Our Mission in Collaboration with the Office of Energy Infrastructure Safety Priority Steward: Chris Porter | Board Members and Energy Safety leadership and management are deepening collaboration and are satisfied with frequency and depth of communication. | Survey of Board Members and Energy Safety leadership | Participate in monthly and quarterly meetings, share information, bring questions | Executive Committee | Monthly meeting | Monthly meeting | Monthly & quarterly meetings | Monthly & quarterly meetings | Monthly & quarterly meetings | Monthly & quarterly meetings | In progress
| Board recommendations are informed by Energy Safety’s approach, timing, and constraints. | Board recommendations are delivered in sync with Energy Safety timelines | Collaborate with Energy Safety staff to understand their processes | Branch Staff | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | Participate in all-hands and management meetings; track WMP review, SCA, and compliance processes | In progress
Priority 2: Building Collaborative Relationships with External Partners Priority Steward: Jessica Block | Board Members and staff have network of partners key to success. | Staff members add contacts to their networks | Staffers attend 4 conferences per year | Branch Staff |  |  |  | Attend NCPA and SCPPA annual conferences |  | Attend CMUA annual conference | Not started
|  | Board makes 4 site visits per year | Staff develops site visits | Branch Staff | Site visit associated with June Board meeting (ArborWorks) |  |  | Site visit associated with September Board meeting (Eaton fire) | Site visit associated with December Board meeting | Site visit associated with March Board meeting | In progress
| Board recommendations are informed by expert advice. | Board makes 4 site visits per year | Board Members attend site visits | Board Members | Site visit associated with June Board meeting (ArborWorks) |  |  | Site visit associated with September Board meeting (Eaton fire) | Site visit associated with December Board meeting | Site visit associated with March Board meeting | In progress
|  | Board presents 4 topical presentations/workshops per year | Board Members contribute contacts and expertise | Board Members |  | Committees work with staff to develop presentation for September Board meeting |  | Committees work with staff to develop presentations for Board meetings | Committees work with staff to develop presentations for Board meetings | Committees work with staff to develop presentations for Board meetings | Not started
|  |  | Staff organize presentations | Branch Staff |  |  |  | Expert presentation to Board at quarterly meeting | Expert presentation to Board at quarterly meeting | Expert presentation to Board at quarterly meeting | In progress
| Board Committees and staff have established and are deepening relationships with external partners. | Branch staff review of relationships | Staff meet with key partners on cadence set by Committees | Branch Staff | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | Monthly and quarterly contacts | In progress
|  |  | Staff review relationships and report to Board | Branch Staff |  | Staff and Committees review relationships | Staff and Committees review relationships | Staff report to Board on external partner relationships | Staff and Committees review relationships | Report to Board on external partner relationships | Not started
| Board and staff have clear priorities for collaborative efforts. | There are clear priorities (and messages where appropriate) for interaction with key partners | Committees identify and review key partners and messages for their workstreams | Workstream Committees |  | Staff and Committees review relationships | Staff and Committees review relationships | Staff report to Board on external partner relationships | Staff and Committees review relationships | Report to Board on external partner relationships | Not started
Priority 3: Retaining and Developing Staff Priority Steward: Mark | Staff are satisfied with their work, work-life balance, recognition, and professional development. | Results of staff survey | Provide each staffer with one or more projects on which they are the lead | Branch Supervisor | Onboard new staffer; identify projects | Ongoing work planning | Ongoing work planning | Ongoing work planning | Ongoing work planning | Ongoing work planning | In progress
|  |  | Build sense of teamwork among staff | Branch Supervisor, Branch Staff | Onboard new staffer; plan teambuilding exercises; collaborate | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | Collaborate; create and execute teambuilding activities | In progress
|  |  | Recognize individual contributions | Branch Supervisor, Branch Staff | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | In branch meetings, ESPD check-ins, Board meetings | Ongoing
|  |  | Encourage and allow time off for vacation and family responsibilities | Branch Supervisor | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Approve staff time off consistent with programmatic needs | Ongoing
|  |  | Maximize benefits of agency RTO policies | Branch Supervisor, Branch Staff | Communicate opportunities and challenges; plan activities | Work through transition to 4 days/week; plan activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | Plan and execute in-person activities | In progress
|  |  | Survey staff semiannually | Branch Supervisor |  | Semiannual survey |  |  | Semiannual survey |  | Not started
| Board Members support staff development | Results of staff survey | Board members introduce staff to members of their networks | Board Members | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Use Committee meetings to identify areas of interest and key contacts; make introductions | Not started
|  |  | Board members use committee meetings and products as staff development opportunities, in collaboration with supervisor | Board Members, Branch Supervisor | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Branch Supervisor identifies development opportunitites and communicates with Board members; Board members work with staff in Committee calls | Not started
| Branch staff develops in capacity to support increased Board effectiveness. | Staffers complete majority of trainings in individual development plans | Staffers identify training goals and opportunities | Branch Staff | Review progress on 2025 IDPs |  |  |  | Develop annual IDP |  | Not started
|  |  | Staffers complete training that aligns with their job responsibilities and career development goals | Branch Staff | As needed and as opportunities arise | As needed and as opportunities arise | As needed and as opportunities arise | As needed and as opportunities arise | As needed and as opportunities arise | As needed and as opportunities arise | In progress
Priority 4: Creating the Structures and Practices for Successful Implementation Priority Steward: Mark | Branch has and follows up-to-date processes, including project management, recordkeeping, and standard operating procedures | Staff meets product deadlines, positioning Board to meet its statutory deadlines | Develop and follow project plans for major work products | Branch Supervisor, Branch Staff | Finalize POU WMP review process and assignments | Execute project plans | Execute project plans | Finalize project plan for 2026 Recommendations to Energy Safety | Execute project plans | Execute project plans | In progress
|  | Website and internal files are clearly organized and up to date | Establish, review, and revise Branch processes, Standard Operating Procedures, and checklists | Branch Supervisor, Branch Staff | Onboard new staffer with SOPs |  |  |  | Review all SOPs; revise as needed |  | Not started
|  | Staff efficiency | Communicate and follow standard processes | Branch Supervisor, Branch Staff | Onboard new staffer with SOPs | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Clear communication between supervisor and staff | Ongoing
| Board focuses attention and resources on clear priorities | Priorities are reflected in Strategic Plan and Work Plans | Board members and staff establish clear priorities | Board, Branch Staff |  |  |  | Review Priorities semiannually at March and September Board meetings |  | Review Priorities semiannually at March and September Board meetings | Not started
|  | Staff resources are aligned with priorities | Supervisor plans staff resources to align with priorities and meet deadlines | Branch Supervisor | Develop annual work plan | Revise work plan as needed with new information | Revise work plan as needed with new information | Update Board on work plan at March and September meetings | Revise work plan as needed with new information | Update Board on work plan at March and September meetings | In progress
|  | Board Member input is focused, clear, and timely | Board members participate in Committee calls | Board Members | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
|  |  | Board members review and provide feedback on documents | Board Members |  |  |  | Board member review of POU Advisory Opinion | Board member review of draft Recommendations to Energy Safety | Board member review of draft Recommendations to Energy Safety | Not started
| Board members are satisfied with frequency and depth of communication with staff | Results of Board Member survey | Staff communicate regular updates to Board and schedule Committee and Board Member briefings | Branch Staff | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing | Ongoing
|  |  | Supervisor conducts survey | Branch Supervisor |  | Semiannual survey |  |  | Semiannual survey |  | Not started
The Wildfire Safety Advisory Board's "2025 - 2027 Strategic Plan" was adopted at the Board's June 4, 2025 meeting.